## Gantt Chart
GANTT Chart for Project "Plan Parade"
| DAY | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ACTIVITY | WBS
Identifier
Get Permits | 3.3.1
Permits Ready | 3.3
Arrange First Aid | 3.2.2
Organize Security | 3.2.1
Safety/ Security Arranged | 3.2
Get Clowns | 3.1.3
Arrange Bands | 3.1.2
Obtain Floats | 3.1.1
Participants Finalized | 3.1
Assemble All Documents | 2.0
Parade Planned | 1.0
LEGEND
Plot of EARLIEST Starts and Finishes
Activity Start
Inspection at start of DAY 8
Activity End
Milestone
Critical Path
Progress