## Sheet1
Activity List for Project "Plan Parade"
WBS | Work | Activity name | Predecessors | Successors | Duration | Leads | Lags | Imposed | Assumptions | Person | Resource | Cost | Estimated
Identifier | Package |  |  |  | Days |  |  | Dates |  | Responsible | Requirements | Code | Cost
1.0 |  | Parade Planned | 2.0 | End | 0 | none | none | none |  | Me | Computer
2.0 | 2.0 | Assemble All Documents | 3.1, 3.2, 3.3 | 1.0 | 5 | none | none | none | There will be no new requirements | Me |  | M.00 | 100
3.1 | 3.1 | Participants Finalized | 3.1.1, 3.1.2, 3.1.3 | 2.0 | 0 | none | none | none | Training will be done | Fred
3.1.1 | 3.1 | Obtain Floats | Start | 3.1 | 5 | none | none | none |  | Fred |  | L.00 | 300
3.1.2 | 3.1 | Arrange Bands | Start | 3.1 | 15 | none | none | none |  | Fred |  | L.00 | 800
3.1.3 | 3.1 | Get Clowns | Start | 3.1 | 5 | none | none | none |  | Fred |  | L.00 | 500
3.2 | 3.2 | Safety/ Security Arranged | 3.2.1, 3.2.2 | 2.0 | 0 | none | none | none | Kits will be available | Sally
3.2.1 | 3.2 | Organize Security | Start | 3.2 | 10 | none | none | none |  | Sally |  | L.00 | 500
3.2.2 | 3.2 | Arrange First Aid | Start | 3.2 | 20 | none | none | none |  | Sally |  | L.00 | 400
3.3 | 3.3 | Permits Ready | 3.3.1 | 2.0 | 0 | none | none | none |  | Joan | Application forms | T.00
3.3.1 | 3.3 | Get Permits | Start | 3.3 | 5 | none | none | Joan not available until Day 2 |  | Joan |  | T.00 | 250