## Sheet1
CPM for Project "Plan Parade"
End of Day
[9 empty] | ES | Dur | EF
Activity
[9 empty] | LS | TF | LF
End of Day
0 | 5 | 5 | [6 empty] | LEGEND
Obtain Floats
15 | 15 | 20
[10 empty] | ES: | Earliest Start
0 | 15 | 15 | 15 | 0 | 15 |  |  |  |  | EF: | Earliest Finish
Arrange Bands |  |  | Particip Final'd | [6 empty] | LS: | Latest Start
5 | 5 | 20 | 20 | 5 | 20 |  |  |  |  | LF: | Latest Finish
[10 empty] | Dur: | Duration
0 | 5 | 5 | [7 empty] | TF: | Total Float
Get Clowns | [11 empty] | the Critical Path
15 | 15 | 20
0 | 10 | 10
Organize Security
10 | 10 | 20 | 20 | 0 | 20 | 20 | 5 | 25 | 25 | 0 | 25
|  |  | Saf'ty/Secur Arr'd |  |  | Assem All Docs |  |  | Parade Planned
0 | 20 | 20 | 20 | 0 | 20 | 20 | 0 | 25 | 25 | 0 | 25
Arrange First Aid
0 | 0 | 20
2 | 5 | 7 | 7 | 0 | 7
Get Permits |  |  | Permits Ready | [5 empty] | EF=ES + Duration
15 | 13 | 20 | 20 | 13 | 20 |  |  |  | LS=LF - Duration
TF=LF - EF