## Sheet1
|  | Activity List for Project "Plan Parade" | [14 empty] | Date: June 1st
[13 empty] | A | B | C | D | E | F
WBS | Work | Activity name | Predecessors | Successors | Duration | Leads | Lags | Imposed | Assumptions | Person | Resource | Cost | Budget | CTD | CTC | TEC | Variances
Identifier | Package |  |  |  | Days |  |  | Dates |  | Responsible | Requirements | Code | Cost |  |  |  | to date | at completion
[16 empty] | B+C | A-B | A-D
1.0 |  | Parade Planned | 2.0 | End | 0 | none | none | none |  | Me | Computer
2.0 | 2.0 | Assemble All Documents | 3.1, 3.2, 3.3 | 1.0 | 5 | none | none | none | There will be no new requirements | Me |  | M.00 | 100 | 0 | 150 | 150 | 100 | -50
3.1 | 3.1 | Participants Finalized | 3.1.1, 3.1.2, 3.1.3 | 2.0 | 0 | none | none | none | Training will be done | Fred
3.1.1 | 3.1 | Obtain Floats | Start | 3.1 | 5 | none | none | none |  | Fred |  | L.00 | 300 | 250 | 0 | 250 | 50 | 50
3.1.2 | 3.1 | Arrange Bands | Start | 3.1 | 15 | none | none | none |  | Fred |  | L.00 | 800 | 500 | 500 | 1000 | 300 | -200
3.1.3 | 3.1 | Get Clowns | Start | 3.1 | 5 | none | none | none |  | Fred |  | L.00 | 500 | 400 | 50 | 450 | 100 | 50
3.2 | 3.2 | Safety/ Security Arranged | 3.2.1, 3.2.2 | 2.0 | 0 | none | none | none | Kits will be available | Sally
3.2.1 | 3.2 | Organize Security | Start | 3.2 | 10 | none | none | none |  | Sally |  | L.00 | 500 | 450 | 150 | 600 | 50 | -100
3.2.2 | 3.2 | Arrange First Aid | Start | 3.2 | 20 | none | none | none |  | Sally |  | L.00 | 400 | 80 | 320 | 400 | 320 | 0
3.3 | 3.3 | Permits Ready | 3.3.1 | 2.0 | 0 | none | none | none |  | Joan | Application forms | T.00
3.3.1 | 3.3 | Get Permits | Start | 3.3 | 5 | none | none | Joan not available until Day 2 |  | Joan |  | T.00 | 250 | 250 | 0 | 250 | 0 | 0
|  | TOTALS | [10 empty] | 2850 | 1930 | 1170 | 3100 | 920 | -250