## Slide 1: HOW TO MAKE A CPM DIAGRAM. Example #1
ACTIVITY BOX
 | End of Day |  |  |  |  |  |  | 
 | End of Day |  |  |  |  |  |  | 
 |  |  |  | ES: |  | Earliest Start |  | 
 |  |  |  | EF: |  | Earliest Finish |  | 
 |  |  |  | LS: |  | Latest Start |  | 
 |  |  |  | LF: |  | Latest Finish |  | 
 |  |  |  | Dur: |  | Duration |  | 
 |  |  |  | TF: |  | Total Float |  | 
ES | Dur | EF
ACTIVITY |  | 
LS | TF | LF
EF=ES + Duration |  |  | 
LS=LF - Duration |  |  | 
TF=LF - EF |  |  | 
Formulas
Notes: This is the Activity Box with its 7 components.

## Slide 2: HOW TO MAKE A CPM DIAGRAM. Example #1
ABBREVIATED ACTIVITY LIST for making a CPM Diagram
Work Package Activity Predecessor Successor Duration (days)
Start up 1 Start 2 0
Start up 2 1 4 3
Start up 4 2 7,5,9 1
A 7 4 8 6
A 8 7 12 1
B 5 4 6 2
B 6 5 12 1
C 9 4 10 8
C 10 9 11 1
C 11 10 12 1
Finish off 12 8,6,11 13 2
Finish off 13 12 Finish 5
How long will
this project
take?
Notes: 1) We will use this Activity List to make our CPM diagram. We will use the Activity attributes shown. How long will this project take? Maybe 31 days? We cannot tell without making a schedule.

## Slide 3: HOW TO MAKE A CPM DIAGRAM. Example #1
 | 0 | 
1 |  | 
Activity 1 has zero days duration. This is a milestone. It has zero duration.
It is the job start, just like the starter’s pistol in a foot race.
Notes: 2) We draw our first Activity box.
3) Insert the Activity number and duration in the box

## Slide 4: HOW TO MAKE A CPM DIAGRAM. Example #1
 | 0 | 
1 |  | 
Notes: 4) Draw the same number of lines from the Activity box as there are Successors. In our case there is one Successor.

## Slide 5: HOW TO MAKE A CPM DIAGRAM. Example #1
 | 0 | 
1 |  | 
Notes: 5) Move down the Activity list to the very next Activity
6) Draw an Activity box for that Activity, at the end of the line from its predecessor

## Slide 6: HOW TO MAKE A CPM DIAGRAM. Example #1
 | 0 |  | 
1 |  |  | 
 | 3 | 
2 |  | 
 | 1 | 
4 |  | 
 | 2 | 
5 |  | 
 | 1 | 
6 |  | 
 | 2 | 
12 |  | 
 | 5 | 
13 |  | 
 | 6 | 
7 |  | 
 | 8 | 
9 |  | 
 | 1 | 
8 |  | 
 | 1 | 
10 |  | 
 | 1 | 
11 |  | 
Notes: 7) Repeat steps 3, 4, 5, 6 until you run out of Activities

## Slide 7: HOW TO MAKE A CPM DIAGRAM. Example #1
0 | 0 | 0
1 |  | 
 | 3 | 3
2 |  | 
 | 1 | 4
4 |  | 
 | 2 | 6
5 |  | 
 | 1 | 7
6 |  | 
 | 2 | 
12 |  | 
 | 5 | 
13 |  | 
 | 6 | 10
7 |  | 
 | 8 | 12
9 |  | 
 | 1 | 11
8 |  | 
 | 1 | 13
10 |  | 
 | 1 | 14
11 |  | 
EF = ES + Duration
Start at Day 0
???
Notes: 8) Start at Day 0 for the first Activity and insert all the Earliest Finishes. What is the EF for Activity 12 ?

## Slide 8: HOW TO MAKE A CPM DIAGRAM. Example #1
0 | 0 | 0
1 |  | 
 | 3 | 3
2 |  | 
 | 1 | 4
4 |  | 
 | 2 | 6
5 |  | 
 | 1 | 7
6 |  | 
 | 2 | 16
12 |  | 
 | 5 | 21
13 |  | 
 | 6 | 10
7 |  | 
 | 8 | 12
9 |  | 
 | 1 | 11
8 |  | 
 | 1 | 13
10 |  | 
 | 1 | 14
11 |  | 
EF = ES + Duration
Notes: 9) Both Activity 11 and Activity 8 must finish before Activity 12. The EF for Activity 11 is 14 days, and the EF for Activity 8 is 11 days. So the EF for Activity 12 will be based upon the EF of Activity 11 because that is the one which will end later.
10) We now see the project will take 21 days according to this plan.

## Slide 9: HOW TO MAKE A CPM DIAGRAM. Example #1
0 | 0 | 0
1 |  | 
 | 3 | 3
2 |  | 
 | 1 | 4
4 |  | 
 | 2 | 6
5 |  | 
 | 1 | 7
6 |  | 
 | 2 | 16
12 |  | 
 | 5 | 21
13 |  | 
 | 6 | 10
7 |  | 
 | 8 | 12
9 |  | 
 | 1 | 11
8 |  | 
 | 1 | 13
10 |  | 
 | 1 | 14
11 |  | 
EF = ES + Duration
PATH C
PATH B
PATH A
Path A = 18 days
Path B = 14 days
Path C = 21 days
Notes: 11) Calculate the length of each path separately, from start to finish. The longest path is Path C and this is called the Critical Path. Path A has 3 days of path slack and Path B has 7 days of path slack.

## Slide 10: HOW TO MAKE A CPM DIAGRAM. Example #1
0 | 0 | 0
1 |  | 
 | 3 | 3
2 |  | 
 | 1 | 4
4 |  | 
 | 2 | 6
5 |  | 
 | 1 | 7
6 |  | 
 | 2 | 16
12 |  | 
 | 5 | 21
13 |  | 
 | 6 | 10
7 |  | 
 | 8 | 12
9 |  | 
 | 1 | 11
8 |  | 
 | 1 | 13
10 |  | 
 | 1 | 14
11 |  | 
EF = ES + Duration
PATH C
PATH B
PATH A
Path A = 18 days
Path B = 14 days
Path C = 21 days
Notes: We will use a red color for the Critical path just to keep track of it.

## Slide 11: HOW TO MAKE A CPM DIAGRAM. Example #1
0 | 0 |  | 0 | 
1 |  |  |  | 
0 | 3 | 3
2 |  | 
3 | 1 | 4
4 |  | 
 | 2 | 6
5 |  | 
 | 1 | 7
6 |  | 
14 | 2 | 16
12 |  | 
16 | 5 | 21
13 |  | 
 | 6 | 10
7 |  | 
4 | 8 | 12
9 |  | 
 | 1 | 11
8 |  | 
12 | 1 | 13
10 |  | 
13 | 1 | 14
11 |  | 
PATH C
PATH B
PATH A
Path A = 18 days
Path B = 14 days
Path C = 21 days
Notes: 12) We will now calculate the Earliest Start (ES) dates for each Activity.
13) First put each ES on the Critical path going from LEFT to RIGHT. The ES is just the EF of the preceeding Activity.

## Slide 12: HOW TO MAKE A CPM DIAGRAM. Example #1
0 | 0 | 0
1 |  | 
0 |  | 0
0 | 3 | 3
2 |  | 
0 |  | 3
3 | 1 | 4
4 |  | 
3 |  | 4
 | 2 | 6
5 |  | 
 | 1 | 7
6 |  | 
14 | 2 | 16
12 |  | 
14 |  | 16
16 | 5 | 21
13 |  | 
16 |  | 21
 | 6 | 10
7 |  | 
4 | 8 | 12
9 |  | 
4 |  | 12
 | 1 | 11
8 |  | 
12 | 1 | 13
10 |  | 
12 |  | 13
13 | 1 | 14
11 |  | 
13 |  | 14
PATH C
PATH B
PATH A
Path A = 18 days
Path B = 14 days
Path C = 21 days
Notes: 14) Still on Critical Path, this time from RIGHT to LEFT, calculate the LATEST Finishes and Starts. Because the Activities are all critical, the latest finishes and starts equal the earliest finishes and starts.

## Slide 13: HOW TO MAKE A CPM DIAGRAM. Example #1
0 | 0 | 0
1 |  | 
0 |  | 0
0 | 3 | 3
2 |  | 
0 |  | 3
3 | 1 | 4
4 |  | 
3 |  | 4
4 | 2 | 6
5 |  | 
6 | 1 | 7
6 |  | 
14 | 2 | 16
12 |  | 
14 |  | 16
16 | 5 | 21
13 |  | 
16 |  | 21
4 | 6 | 10
7 |  | 
4 | 8 | 12
9 |  | 
4 |  | 12
10 | 1 | 11
8 |  | 
12 | 1 | 13
10 |  | 
12 |  | 13
13 | 1 | 14
11 |  | 
13 |  | 14
PATH C
PATH B
PATH A
Path A = 18 days
Path B = 14 days
Path C = 21 days
Notes: 15) Calculate dates for the ES for Activities not on the Critical Path. Going from LEFT to RIGHT. Starting from the launching point off the Critical Path.
in our case this will be Path A and Path B. The ES will simply be the EF of its predecessor.

## Slide 14: HOW TO MAKE A CPM DIAGRAM. Example #1
0 | 0 | 0
1 |  | 
0 |  | 0
0 | 3 |  | 3
2 |  |  | 
0 |  |  | 3
3 | 1 | 4
4 |  | 
3 |  | 4
4 | 2 | 6
5 |  | 
11 |  | 13
6 | 1 | 7
6 |  | 
13 |  | 14
14 | 2 | 16
12 |  | 
14 |  | 16
16 | 5 | 21
13 |  | 
16 |  | 21
4 | 6 | 10
7 |  | 
7 |  | 13
4 | 8 | 12
9 |  | 
4 |  | 12
10 | 1 | 11
8 |  | 
13 |  | 14
12 | 1 | 13
10 |  | 
12 |  | 13
13 | 1 | 14
11 |  | 
13 |  | 14
LS = LF - Duration
PATH C
PATH B
PATH A
Path A = 18 days
Path B = 14 days
Path C = 21 days
Notes: 16) Finally calculate the latest dates for the non-Critical Activities. (not on Critical path). Go from RIGHT to LEFT.
17) Simply subtract the durations from the LF to get the LS for each Activity.
18) Continue calculating until all the ES’s, EF’s, LS’s, and LF’s are filled in for every Activity.

## Slide 15: HOW TO MAKE A CPM DIAGRAM. Example #1
0 | 0 | 0
1 |  | 
0 | 0 | 0
0 | 3 | 3
2 |  | 
0 | 0 | 3
3 | 1 | 4
4 |  | 
3 | 0 | 4
4 | 2 | 6
5 |  | 
11 | 7 | 13
6 | 1 | 7
6 |  | 
13 | 7 | 14
14 | 2 | 16
12 |  | 
14 | 0 | 16
16 | 5 | 21
13 |  | 
16 | 0 | 21
4 | 6 | 10
7 |  | 
7 | 3 | 13
4 | 8 | 12
9 |  | 
4 | 0 | 12
10 | 1 | 11
8 |  | 
13 | 3 | 14
12 | 1 | 13
10 |  | 
12 | 0 | 13
13 | 1 | 14
11 |  | 
13 | 0 | 14
TF = LF - EF
PATH C
PATH B
PATH A
Path A = 18 days
Path B = 14 days
Path C = 21 days
Notes: 19) Calculate the Total Float for each Activity. The formula is TF=LF-EF.
This is your completed CPM diagram. You may wish to print it out. We will analyze this CPM diagram to learn more about this project.